## Control
Field | Tomas baseline | QC review
Prepared by | Tomas Li, QC Stability
Prepared | 2027-02-05
Study | STB-AVI401-002
Product / condition | AVI-401 / 25 C, 60% RH
Pull | 24 months / 2027-03-01
Working revision | 0.4 — for QC functional approval
QC reviewer | Viktor Takacs
QC disposition
Decision date
Overall restriction
Working basis | All three registration lots will be pulled on 1 March. Testing is planned inside the normal completion window, and the current calibration package is taken to support the study chain through the regulatory update. The 24-month dataset is expected to support the open authority response and COM-AVI401-008.

## Pull Plan
Lot | Presentation | Pull | Planned start | Planned completion | Tomas baseline | QC status | QC rationale / send-back | Action owner | Due / hold point | Evidence to close | QC comment ref
AVI401-R01 | 100 mL | 2027-03-01 | 2027-03-02 | 2027-04-14 | Authorized — chamber calibration is current and all work is within the routine testing window.
AVI401-R02 | 250 mL | 2027-03-01 | 2027-03-02 | 2027-04-14 | Authorized — 250 mL remains the worst-case presentation and will lead the regulatory dataset.
AVI401-R03 | 500 mL | 2027-03-01 | 2027-03-02 | 2027-04-14 | Authorized — no lot-specific dependency identified.

## Execution Sequence
Activity | Method / asset | Lots | Planned start | Planned complete | Tomas baseline | QC status | QC rationale / send-back | Action owner | Due / hold point | Evidence to close | QC comment ref
Sample pull and receipt | CHM-25-03 | R01 / R02 / R03 | 2027-03-01 | 2027-03-01 | Ready — annual chamber calibration is current to 5 December 2027.
Appearance and pH | MTH-VIS-002 / MTH-PHY-004 | R01 / R02 / R03 | 2027-03-02 | 2027-03-04 | Ready — routine bench sequence.
Assay | MTH-HPLC-011 / HPLC-04 / RS-AVR-014 | R01 / R02 / R03 | 2027-03-15 | 2027-03-18 | Ready — the avericin standard certificate became effective 3 May 2025 and supports the March campaign.
Impurities | MTH-HPLC-012 / HPLC-04 / RS-AVR-014 | R01 / R02 / R03 | 2027-03-22 | 2027-03-26 | Ready — method revalidation remains current through June and the same standard is already approved for the study.
Osmolality | MTH-PHY-009 / OSM-02 / RS-OSM-004 | R01 / R02 / R03 | 2027-03-08 | 2027-03-10 | Ready — standard remains within assigned life.
Particulate matter | MTH-PHY-015 / PM-01 / RS-PSL-012 | R01 / R02 / R03 | 2027-03-08 | 2027-03-12 | Ready — no open dependency.
Container closure integrity | MTH-CCI-003 / CCI-02 | R01 / R02 / R03 | 2027-04-13 | 2027-04-14 | Ready — the April calibration anniversary is inside the routine scheduling month.
Sterility | MTH-MIC-001 / INC-03 | R01 / R02 / R03 | 2027-03-02 | 2027-03-16 | Ready — incubation and review fit the response plan.
Independent review and dataset lock | LIMS / controlled laboratory notebook | R01 / R02 / R03 | 2027-03-17 | 2027-03-19 | On track — lock after primary results; late CCI data can follow under the commitment update.

## Chain and Controls
Dependency | Function | Baseline evidence | Baseline validity | Planned use | Tomas baseline | QC status | QC rationale / send-back | Action owner | Due / hold point | Evidence to close | QC comment ref
CHM-25-03 | 25 C / 60% RH storage | MER-2026-4587 calibration certificate | 2027-12-05 | 2027-03-01 pull | Current; annual calibration demonstrates qualified state.
RS-AVR-014 | Assay and impurities standard | AVT-RS-088 effective 2025-05-03 | 2027-05-03 | 2027-03-15 to 2027-03-26 | Current through the planned HPLC campaign.
CCI-02 | Vacuum-decay CCI testing | MER-2026-5512 | April 2027 | 2027-04-13 to 2027-04-14 | Current; work inside the due month is acceptable.
RS-OSM-004 | Osmolality calibration standard | AVT-RS-093 | 2027-05-08 | 2027-03-08 to 2027-03-10 | Current for planned use.
MTH-HPLC-012 | Impurities method | AVT-VAL-352 | 2027-06-30 | 2027-03-22 to 2027-03-26 | Current for 24-month testing; periodic action can remain on the annual plan.
UV-02 / GC-01 / KF-01 | General laboratory instruments | Current asset register | Various 2027 dates | Contingency availability | Include in chain clearance because they are laboratory backup assets.

## Regulatory Handoff
Milestone / request | External date | Planned QC handoff | Owner | Tomas baseline | Source package / status | QC status | QC rationale / send-back | Action owner | Due / hold point | Evidence to close | QC comment ref
HA-AVI401-IR-2027-014 written response | 2027-03-20 | 2027-03-19 | Regulatory CMC | Supply the complete verified 24-month result set with the written response. | 24-month pull plan; long-term results workbook
COM-AVI401-008 stability update | 2027-04-30 | 2027-03-19 | Regulatory CMC | Use the same locked package as the information-request response; no separate QC milestone is required. | 24-month pull plan; RIM commitment
Per-lot Impurity A projections and residual error | 2027-03-20 | 2027-03-17 | QC Stability | Refresh after the 24-month point and confirm the 250 mL presentation remains worst case. | Long-term results workbook; current trend workbook
Accelerated Impurity A significant-change handling | 2027-03-20 | 2027-03-12 | QC Stability | No separate action: results remain within specification. | Accelerated/intermediate workbook
Invalidated Impurity B run and campaign impact | 2027-03-20 | 2027-03-12 | QC Stability | Provide the replacement result; no additional campaign assessment is needed. | Laboratory investigation and replacement result
Overwrap oxygen transmission and headspace support | 2027-03-20 | 2027-03-12 | MSAT / Regulatory CMC | Reference the current stability summary as confirmation of package control. | Current stability summary

## Review Actions
Action ID | Linked sheet / cell | QC finding or restriction | Owner | Due | Hold point / consequence | Required evidence | Status | Closure comment | QC reviewer
QC-01
QC-02
QC-03
QC-04
QC-05
QC-06
QC-07
QC-08
QC-09
QC-10
QC-11
QC-12
QC-13
QC-14
QC-15

## QC Disposition
Decision field | QC entry
Disposition
Decision date
Reviewer | Viktor Takacs
Scope approved
Restrictions
Pull authorization
Dataset release
Regulatory handoff
Open action IDs
Evidence basis
QA consultation
Decision statement