## Control
Field | Tomas baseline | QC review
Prepared by | Tomas Li, QC Stability
Prepared | 2027-02-05
Study | STB-AVI401-002
Product / condition | AVI-401 / 25 C, 60% RH
Pull | 24 months / 2027-03-01
Working revision | 0.4 — for QC functional approval | 0.4 reviewed; not approved. Return as 0.5 after QC-01 to QC-14 close.
QC reviewer | Viktor Takacs
QC disposition |  | Not approved - returned for correction (hold).
Decision date |  | 2027-02-08
Overall restriction |  | Pull authorization, dataset release and regulatory handoff withheld. See Review Actions QC-01 to QC-15 and the QC Disposition sheet.
Working basis | All three registration lots will be pulled on 1 March. Testing is planned inside the normal completion window, and the current calibration package is taken to support the study chain through the regulatory update. The 24-month dataset is expected to support the open authority response and COM-AVI401-008. | QC review does not accept the working basis as written. The 24-month dataset is not the answer to the open authority letter: HA-AVI401-IR-2027-014 point 7 routes it to COM-AVI401-008. The calibration/qualification package also does not clear the testing chain: CHM-25-03 requalification (QC-02), RS-AVR-014 expiry (QC-03) and CCI-02 calibration (QC-04) are not supported as stated, and the chain list is incomplete (QC-12).
Note on B12: SEND-BACK (Viktor Takacs, QC, 2027-02-08): baseline working basis superseded by QC-06, QC-07, QC-02/03/04 and QC-12. Do not use it to authorize the pull or the handoff.

## Pull Plan
Lot | Presentation | Pull | Planned start | Planned completion | Tomas baseline | QC status | QC rationale / send-back | Action owner | Due / hold point | Evidence to close | QC comment ref
AVI401-R01 | 100 mL | 2027-03-01 | 2027-03-02 | 2027-04-14 | Authorized — chamber calibration is current and all work is within the routine testing window. | Hold - lot mapping correct, authorization withheld. | AVI401-R01 is correctly listed as 100 mL. The pull is not authorized because the testing-chain clearance is not complete (QC-12) and the chamber qualified state is not established (QC-02). | Tomas Li, QC Stability | 2027-02-26 | Complete chain clearance and chamber qualified-state evidence (QC-02, QC-12). | QC-01, QC-02, QC-12
AVI401-R02 | 250 mL | 2027-03-01 | 2027-03-02 | 2027-04-14 | Authorized — 250 mL remains the worst-case presentation and will lead the regulatory dataset. | Not approved - wrong presentation. | AVI401-R02 is 100 mL in the study source (Long_Term_Results Lots, 3.2.P.8, AVT-STB-301), not 250 mL. The '250 mL worst-case' attribution is on the wrong lot. Correct to 100 mL. | Tomas Li, QC Stability | 2027-02-26 | Corrected lot-to-presentation mapping reconciled to LIMS/study source (QC-01). | QC-01
AVI401-R03 | 500 mL | 2027-03-01 | 2027-03-02 | 2027-04-14 | Authorized — no lot-specific dependency identified. | Not approved - wrong presentation and worst-case missed. | AVI401-R03 is the 250 mL presentation (and the worst-case oxidative lot), not 500 mL. No 500 mL presentation exists in the registration. Correct the mapping and identify R03 as the lot leading the regulatory dataset. | Tomas Li, QC Stability | 2027-02-26 | Corrected lot-to-presentation mapping; R03 identified as 250 mL worst-case (QC-01). | QC-01
Note on B3: SEND-BACK (Viktor Takacs, QC, 2027-02-08): source records (Lots sheet; 3.2.P.8; AVT-STB-301) state AVI401-R02 is 100 mL. Baseline entry is wrong. See QC-01.
Note on B4: SEND-BACK (Viktor Takacs, QC, 2027-02-08): AVI401-R03 is the 250 mL worst-case lot, not 500 mL. No 500 mL presentation is registered. See QC-01.

## Execution Sequence
Activity | Method / asset | Lots | Planned start | Planned complete | Tomas baseline | QC status | QC rationale / send-back | Action owner | Due / hold point | Evidence to close | QC comment ref
Sample pull and receipt | CHM-25-03 | R01 / R02 / R03 | 2027-03-01 | 2027-03-01 | Ready — annual chamber calibration is current to 5 December 2027. | Not approved - wrong qualified-state basis. | AVT-STB-102-A4 makes requalification under AVT-SOP-045 (36-month interval) the governing activity for the stability chamber, not the annual calibration certificate. The last requalification on file is CC-2023-004 (2023); it lapses before the 2027-03-01 pull. MER-2026-4587 (calibration due 2027-12-05) does not substitute. | Validation (with QC Stability) | 2027-02-26 | Current CHM-25-03 requalification record/qualification summary before the pull (QC-02). | QC-02
Appearance and pH | MTH-VIS-002 / MTH-PHY-004 | R01 / R02 / R03 | 2027-03-02 | 2027-03-04 | Ready — routine bench sequence. | Baseline methods current; chain entry incomplete. | MTH-VIS-002 (AVT-VAL-358, 2025-06-12) and MTH-PHY-004 (AVT-VAL-348, 2025-02-10) are current. The pH chain assets PH-03 (cal. 2026-09-20) and RS-BUF-021 (expiry 2027-10-11) are missing from Chain and Controls, so the chain is not cleared. | Tomas Li, QC Stability | 2027-02-26 | Complete chain entries for PH-03 and RS-BUF-021 (QC-12). | QC-12
Assay | MTH-HPLC-011 / HPLC-04 / RS-AVR-014 | R01 / R02 / R03 | 2027-03-15 | 2027-03-18 | Ready — the avericin standard certificate became effective 3 May 2025 and supports the March campaign. | Not approved - standard expiry misstated; chain incomplete. | RS-AVR-014 expires 2027-03-19 (AVT-RS-088: qualified 2025-03-19). 2025-05-03 is the certificate effective date, not the expiry. Assay is planned 2027-03-15 to 03-18 and is inside expiry only if it completes by 2027-03-19. HPLC-04 calibration MER-2026-8014 (2026-10-05, due 2027-10-05) is current but omitted from Chain and Controls. | Tomas Li, QC Stability | 2027-03-19 | Corrected RS-AVR-014 expiry; assay completed inside expiry; HPLC-04 added to the chain (QC-03, QC-12). | QC-03, QC-12
Impurities | MTH-HPLC-012 / HPLC-04 / RS-AVR-014 | R01 / R02 / R03 | 2027-03-22 | 2027-03-26 | Ready — method revalidation remains current through June and the same standard is already approved for the study. | Not approved - standard expires before campaign. | Impurities is planned 2027-03-22 to 03-26, after the RS-AVR-014 expiry of 2027-03-19. A requalified or replacement avericin standard must be in place, or the campaign rescheduled inside expiry. RS-IMPA-009 (2028-03-14) and RS-IMPB-006 (2028-01-31) are current, and MTH-HPLC-012 revalidation AVT-VAL-352 (2022-06-30, 60-month) is current to 2027-06-30. | Tomas Li, QC Stability | 2027-03-19 | Requalified/replacement avericin standard certificate or revised schedule inside expiry (QC-03). | QC-03
Osmolality | MTH-PHY-009 / OSM-02 / RS-OSM-004 | R01 / R02 / R03 | 2027-03-08 | 2027-03-10 | Ready — standard remains within assigned life. | Baseline current; chain entry incomplete. | OSM-02 calibration 2026-11-02 (due 2027-11-02), RS-OSM-004 expiry 2027-05-08 and MTH-PHY-009 revalidation AVT-VAL-344 (2023-11-05) are all current. Add OSM-02, RS-OSM-004 and MTH-PHY-009 to Chain and Controls. | Tomas Li, QC Stability | 2027-02-26 | Complete chain entries (QC-12). | QC-12
Particulate matter | MTH-PHY-015 / PM-01 / RS-PSL-012 | R01 / R02 / R03 | 2027-03-08 | 2027-03-12 | Ready — no open dependency. | Baseline current; chain entry incomplete. | PM-01 calibration 2026-12-01 (due 2027-12-01), RS-PSL-012 expiry 2028-06-02 and MTH-PHY-015 revalidation AVT-VAL-355 (2024-08-22) are current. Add PM-01, RS-PSL-012 and MTH-PHY-015 to Chain and Controls. | Tomas Li, QC Stability | 2027-02-26 | Complete chain entries (QC-12). | QC-12
Container closure integrity | MTH-CCI-003 / CCI-02 | R01 / R02 / R03 | 2027-04-13 | 2027-04-14 | Ready — the April calibration anniversary is inside the routine scheduling month. | Not approved - calibration expires before test. | CCI-02 calibration MER-2026-5512 was performed 2026-04-12; the 12-month interval expires 2027-04-12. CCI testing is 2027-04-13 to 04-14, outside the qualified interval. 'Inside the due month' is not supported by AVT-STB-102-A4. | Engineering and Facilities (with QC Stability) | 2027-04-12 | CCI-02 recalibration certificate effective before 2027-04-13, or a rescheduled CCI within the qualified interval (QC-04). | QC-04
Sterility | MTH-MIC-001 / INC-03 | R01 / R02 / R03 | 2027-03-02 | 2027-03-16 | Ready — incubation and review fit the response plan. | Baseline current; chain entry incomplete. | INC-03 calibration 2026-12-19 (due 2027-12-19) and MTH-MIC-001 revalidation AVT-VAL-347 (2024-01-18) are current. Add INC-03 and MTH-MIC-001 to Chain and Controls. | Tomas Li, QC Stability | 2027-02-26 | Complete chain entries (QC-12). | QC-12
Independent review and dataset lock | LIMS / controlled laboratory notebook | R01 / R02 / R03 | 2027-03-17 | 2027-03-19 | On track — lock after primary results; late CCI data can follow under the commitment update. | Not approved - lock before data complete. | The 2027-03-19 lock precedes impurities completion (2027-03-26) and CCI (2027-04-13/14). A complete verified 24-month dataset cannot be locked then. Late CCI data under a commitment update does not make the released dataset complete. | Tomas Li, QC Stability | 2027-04-14 | Revised lock date after the last 24-month result is verified, or a documented partial scope with controlled follow-up (QC-05). | QC-05
Note on F2: SEND-BACK (Viktor Takacs, QC, 2027-02-08): annual calibration is not the governing qualified-state activity for CHM-25-03. See QC-02.
Note on F4: SEND-BACK (Viktor Takacs, QC, 2027-02-08): RS-AVR-014 expires 2027-03-19; 2025-05-03 is the effective date. See QC-03.
Note on F5: SEND-BACK (Viktor Takacs, QC, 2027-02-08): impurities campaign runs after RS-AVR-014 expiry (2027-03-19). See QC-03.
Note on F8: SEND-BACK (Viktor Takacs, QC, 2027-02-08): CCI-02 expires 2027-04-12; test is 2027-04-13/14. See QC-04.
Note on F10: SEND-BACK (Viktor Takacs, QC, 2027-02-08): lock on 2027-03-19 precedes impurities and CCI results. See QC-05.

## Chain and Controls
Dependency | Function | Baseline evidence | Baseline validity | Planned use | Tomas baseline | QC status | QC rationale / send-back | Action owner | Due / hold point | Evidence to close | QC comment ref
CHM-25-03 | 25 C / 60% RH storage | MER-2026-4587 calibration certificate | 2027-12-05 | 2027-03-01 pull | Current; annual calibration demonstrates qualified state. | Not approved - wrong governing activity. | The chamber's qualified state is established by requalification under AVT-SOP-045 at a 36-month interval (AVT-STB-102-A4). The last requalification on file is CC-2023-004 (2023); it lapses before the 2027-03 pull. MER-2026-4587 (annual calibration, due 2027-12-05) is not the governing evidence. | Validation (with QC Stability) | 2027-02-26 | Current CHM-25-03 requalification record (QC-02). | QC-02
RS-AVR-014 | Assay and impurities standard | AVT-RS-088 effective 2025-05-03 | 2027-05-03 | 2027-03-15 to 2027-03-26 | Current through the planned HPLC campaign. | Not approved - expiry misstated. | RS-AVR-014 expiry is 2027-03-19 (AVT-RS-088). The baseline shows 2027-05-03, which is the certificate effective date plus two years and is not the assigned expiry. The impurities campaign uses this standard after expiry. | Tomas Li, QC Stability | 2027-03-19 | Corrected expiry and requalified/replacement standard before use (QC-03). | QC-03
CCI-02 | Vacuum-decay CCI testing | MER-2026-5512 | April 2027 | 2027-04-13 to 2027-04-14 | Current; work inside the due month is acceptable. | Not approved - calibration expires before use. | CCI-02 calibration MER-2026-5512 (2026-04-12) expires 2027-04-12. CCI testing is 2027-04-13 to 04-14, outside the qualified interval. 'Inside the due month' is not the interval rule in AVT-STB-102-A4. | Engineering and Facilities (with QC Stability) | 2027-04-12 | CCI-02 recalibration before use or rescheduled CCI (QC-04). | QC-04
RS-OSM-004 | Osmolality calibration standard | AVT-RS-093 | 2027-05-08 | 2027-03-08 to 2027-03-10 | Current for planned use. | Verified current - baseline accepted. | RS-OSM-004 qualification AVT-RS-093 assigns expiry 2027-05-08, which covers the planned use 2027-03-08 to 03-10. QC-12 requires this asset to be added to the chain list. | Tomas Li, QC Stability | 2027-02-26 | Add RS-OSM-004 to the complete chain list (QC-12). | QC-12
MTH-HPLC-012 | Impurities method | AVT-VAL-352 | 2027-06-30 | 2027-03-22 to 2027-03-26 | Current for 24-month testing; periodic action can remain on the annual plan. | Verified current - baseline accepted. | MTH-HPLC-012 revalidation AVT-VAL-352 was performed 2022-06-30; the 60-month interval runs to 2027-06-30 and covers the planned use. The RS-AVR-014 expiry issue is separate (QC-03). | Tomas Li, QC Stability | 2027-02-26 | Retain AVT-VAL-352 evidence; correct the standard entry (QC-03, QC-12). | QC-03, QC-12
UV-02 / GC-01 / KF-01 | General laboratory instruments | Current asset register | Various 2027 dates | Contingency availability | Include in chain clearance because they are laboratory backup assets. | Not approved - out of scope; remove. | UV-02, GC-01 and KF-01 serve no method in AVT-SPEC-018 and are not part of the STB-AVI401-002 testing chain under AVT-STB-102-A4. Including backup assets inflates the chain and hides the real gaps (PH-03, HPLC-04, OSM-02, PM-01, INC-03, RS-BUF-021, RS-IMPA-009, RS-IMPB-006, RS-PSL-012 and the method revalidations). | Tomas Li, QC Stability | 2027-02-26 | Remove out-of-scope assets and list the complete chain with qualified-state evidence (QC-12). | QC-12
Note on F2: SEND-BACK (Viktor Takacs, QC, 2027-02-08): requalification under AVT-SOP-045 governs; last on file is CC-2023-004. See QC-02.
Note on F3: SEND-BACK (Viktor Takacs, QC, 2027-02-08): RS-AVR-014 expiry is 2027-03-19 (AVT-RS-088), not 2027-05-03. See QC-03.
Note on F4: SEND-BACK (Viktor Takacs, QC, 2027-02-08): CCI-02 expires 2027-04-12; test is 2027-04-13/14. See QC-04.
Note on F7: SEND-BACK (Viktor Takacs, QC, 2027-02-08): UV-02, GC-01 and KF-01 are outside the testing chain (AVT-STB-102-A4). See QC-12.

## Regulatory Handoff
Milestone / request | External date | Planned QC handoff | Owner | Tomas baseline | Source package / status | QC status | QC rationale / send-back | Action owner | Due / hold point | Evidence to close | QC comment ref
HA-AVI401-IR-2027-014 written response | 2027-03-20 | 2027-03-19 | Regulatory CMC | Supply the complete verified 24-month result set with the written response. | 24-month pull plan; long-term results workbook | Not approved - scope and timing wrong. | HA-AVI401-IR-2027-014 point 7 states the 24-month pull is not part of sequence 0003 and is to be provided under COM-AVI401-008; no earlier pull is requested for the letter. The written response due 2027-03-20 must answer points 1-6 from existing records. It cannot and need not supply the 24-month dataset. | Sofia Ortega, Regulatory CMC (with QC Stability) | 2027-03-20 | Point-by-point IR response from approved records; separate routing of the 24-month data to COM-AVI401-008 (QC-06). | QC-06
COM-AVI401-008 stability update | 2027-04-30 | 2027-03-19 | Regulatory CMC | Use the same locked package as the information-request response; no separate QC milestone is required. | 24-month pull plan; RIM commitment | Not approved - package cannot be complete by 2027-03-19. | The commitment update must carry the verified 24-month dataset. Impurities complete 2027-03-26 and CCI on 2027-04-13/14, so a 2027-03-19 lock cannot produce a complete package. A separate QC verification milestone is required before the 2027-04-30 commitment date. | Sofia Ortega, Regulatory CMC (with QC Stability) | 2027-04-30 | Revised COM-AVI401-008 milestone plan with QC verification after all 24-month results (QC-05, QC-07). | QC-05, QC-07
Per-lot Impurity A projections and residual error | 2027-03-20 | 2027-03-17 | QC Stability | Refresh after the 24-month point and confirm the 250 mL presentation remains worst case. | Long-term results workbook; current trend workbook | Not approved - deferred and mis-scoped. | IR point 2 requires the linear (or justified) projection of Impurity A to 24 and 36 months per lot, the residual standard error and a worst-case discussion, and the supported shelf life if the one-sided confidence bound crosses 0.50% before 36 months. The workbook defers this to a post-24-month refresh and attributes worst case to the wrong lot. | Tomas Li, QC Stability (with Regulatory CMC) | 2027-03-20 | Per-lot Impurity A projection with residual standard error, worst-case discussion for R03 (250 mL) and shelf-life statement (QC-08). | QC-08
Accelerated Impurity A significant-change handling | 2027-03-20 | 2027-03-12 | QC Stability | No separate action: results remain within specification. | Accelerated/intermediate workbook | Not approved - significant-change handling not confirmed. | Accelerated Impurity A on AVI401-R03 reached 0.46% at 6 months (from 0.06%), a significant change under ICH Q1A(R2); 'within specification' is not the test. IR point 4 asks to confirm the significant-change treatment and that STB-AVI401-003 is the complete response. 3.2.P.8 says the intermediate study was initiated because of the accelerated change, while AVT-STB-301 says it was a standing zone II precaution 'not in response to a finding'. | Tomas Li, QC Stability (with Regulatory CMC) | 2027-03-20 | Significant-change assessment and reconciled intermediate-study rationale (QC-09). | QC-09
Invalidated Impurity B run and campaign impact | 2027-03-20 | 2027-03-12 | QC Stability | Provide the replacement result; no additional campaign assessment is needed. | Laboratory investigation and replacement result | Not approved - campaign impact omitted. | IR point 4 asks for the assignable cause of LAB-2025-114, the confirmatory replacement result, and whether the same mobile-phase error could have affected any other reported sequence in the campaign. The workbook states no campaign assessment is needed, which does not answer the question. | Quality Investigations (with QC Stability) | 2027-03-20 | LAB-2025-114 investigation, campaign/sequence impact review and confirmatory result (QC-10). | QC-10
Overwrap oxygen transmission and headspace support | 2027-03-20 | 2027-03-12 | MSAT / Regulatory CMC | Reference the current stability summary as confirmation of package control. | Current stability summary | Not approved - response incomplete; open change. | IR point 3 asks for the OTR used for registered overwrap BF-51 at a humidity relevant to 25 C/60% RH and for how residual headspace oxygen in the 100 mL and 250 mL fills was controlled or measured, with document and page if held elsewhere. The workbook cites only the stability summary. Open CC-AVI401-017 proposes alternate HF-55 (OTR 3.8 vs BF-51 2.4 at 23 C/65% RH) but is not approved or authorized and must not be represented as the registered package. | MSAT (with Regulatory CMC and QC Stability) | 2027-03-20 | Document/page citation for BF-51 OTR and residual-headspace control/measurement; confirmation of registered overwrap and CC-AVI401-017 status (QC-11). | QC-11
Note on E2: SEND-BACK (Viktor Takacs, QC, 2027-02-08): IR point 7 routes the 24-month data to COM-AVI401-008; answer points 1-6 from existing records. See QC-06.
Note on E3: SEND-BACK (Viktor Takacs, QC, 2027-02-08): 24-month package cannot be complete by 2027-03-19 (impurities 2027-03-26; CCI 2027-04-14). See QC-05/QC-07.
Note on E4: SEND-BACK (Viktor Takacs, QC, 2027-02-08): provide per-lot projection with residual error and correct worst-case lot (R03, 250 mL). See QC-08.
Note on E5: SEND-BACK (Viktor Takacs, QC, 2027-02-08): confirm ICH significant-change treatment; reconcile 3.2.P.8 with AVT-STB-301. See QC-09.
Note on E6: SEND-BACK (Viktor Takacs, QC, 2027-02-08): assess whether the LAB-2025-114 mobile-phase error affected other sequences. See QC-10.
Note on E7: SEND-BACK (Viktor Takacs, QC, 2027-02-08): cite BF-51 OTR and headspace evidence; do not reference unapproved HF-55 (CC-AVI401-017). See QC-11.

## Review Actions
Action ID | Linked sheet / cell | QC finding or restriction | Owner | Due | Hold point / consequence | Required evidence | Status | Closure comment | QC reviewer
QC-01 | Pull Plan!B2:B4, F2:F4; Long_Term_Results!Lots | Lot/presentation mapping is wrong. Source records (Long_Term_Results Lots; 3.2.P.8; AVT-STB-301) show AVI401-R01 = 100 mL, AVI401-R02 = 100 mL, AVI401-R03 = 250 mL. The workbook shows R02 = 250 mL and R03 = 500 mL; no 500 mL presentation exists. The 250 mL worst-case lot is R03, not R02. | Tomas Li, QC Stability | 2027-02-26 | Pull authorization withheld; the regulatory worst-case discussion is wrong until corrected. | Corrected lot-to-presentation mapping reconciled to LIMS/study source; R03 identified as the 250 mL worst-case lot; revised Pull Plan. | Open |  | Viktor Takacs
QC-02 | Execution Sequence!A2:F2; Chain and Controls!A2:F2 | CHM-25-03 qualified state is not established against the governing activity. AVT-STB-102-A4 makes requalification under AVT-SOP-045 (36-month interval) governing for a stability chamber. The last requalification on file is CC-2023-004 (2023); the annual calibration certificate MER-2026-4587 (due 2027-12-05) does not substitute. The chamber appears out of qualified state for the 2027-03 pull. | Validation (with QC Stability) | 2027-02-26 | Pull authorization withheld; results generated in an unqualified chamber are not releasable. | Current CHM-25-03 requalification qualification summary/record, or completed requalification before the pull. | Open |  | Viktor Takacs
QC-03 | Execution Sequence!B4:F5; Chain and Controls!A3:F3 | RS-AVR-014 expiry is misstated. AVT-RS-088 records qualification on 2025-03-19 and expiry 2027-03-19; 2025-05-03 is the certificate effective date. The impurities campaign 2027-03-22 to 03-26 runs after expiry, and the assay campaign 2027-03-15 to 03-18 is inside expiry only if completed by 2027-03-19. | Tomas Li, QC Stability | 2027-03-19 | Impurities testing withheld; use of an expired quantitative standard invalidates results. | Requalified/replacement avericin reference standard certificate, or revised schedule inside expiry; corrected expiry in Chain and Controls. | Open |  | Viktor Takacs
QC-04 | Execution Sequence!B8:F8; Chain and Controls!A4:F4 | CCI-02 calibration MER-2026-5512 was performed 2026-04-12; the 12-month interval expires 2027-04-12. CCI testing is planned 2027-04-13 to 04-14, outside the qualified interval. 'Inside the due month' is not supported by AVT-STB-102-A4. | Engineering and Facilities (with QC Stability) | 2027-04-12 | CCI testing withheld; the 24-month CCI result cannot be reported. | CCI-02 recalibration certificate effective before 2027-04-13, or a rescheduled CCI within the qualified interval. | Open |  | Viktor Takacs
QC-05 | Execution Sequence!A10:E10; Regulatory Handoff!A3 | Dataset lock on 2027-03-19 precedes impurities completion (2027-03-26) and CCI (2027-04-13/14). A complete verified 24-month result set cannot exist at lock. Late CCI data under a commitment update is not a substitute for a complete dataset. | Tomas Li, QC Stability | 2027-04-14 | Dataset release and COM-AVI401-008 update withheld until all 24-month tests are verified. | Revised lock date after the last 24-month result is verified, and the verification record; or a documented partial scope with controlled follow-up. | Open |  | Viktor Takacs
QC-06 | Regulatory Handoff!A2:F2 | Written-response scope is wrong. IR point 7 states the 24-month pull is not part of sequence 0003 and is to be provided under COM-AVI401-008; no earlier pull is requested for the letter. The response due 2027-03-20 must answer points 1-6 from existing records. The workbook also does not decompose points 1, 5 and 6. | Sofia Ortega, Regulatory CMC (with QC Stability) | 2027-03-20 | Regulatory handoff withheld; authority deadline at risk. | Point-by-point IR response mapped to approved records; separate routing of the 24-month update to COM-AVI401-008. | Open |  | Viktor Takacs
QC-07 | Regulatory Handoff!A3:F3 | COM-AVI401-008 is scheduled to reuse a package locked 2027-03-19, before the 24-month dataset is complete. A separate QC verification milestone is required after all 24-month results are verified and before the 2027-04-30 commitment date. | Sofia Ortega, Regulatory CMC (with QC Stability) | 2027-04-30 | Commitment update withheld. | Revised commitment milestone plan showing data availability, QC verification and submission. | Open |  | Viktor Takacs
QC-08 | Regulatory Handoff!A4:F4 | IR point 2 requires a linear (or justified) projection of Impurity A to 24 and 36 months for each lot, the residual standard error and a worst-case discussion; if the one-sided confidence bound crosses 0.50% before 36 months, the supported shelf life and additional evidence must be stated. The workbook defers this to a post-24-month refresh and mis-identifies the worst-case lot. | Tomas Li, QC Stability (with Regulatory CMC) | 2027-03-20 | IR response incomplete. | Per-lot Impurity A projection with residual standard error, worst-case discussion for R03 (250 mL), and supported shelf-life statement. | Open |  | Viktor Takacs
QC-09 | Regulatory Handoff!A5:F5; 3.2.P.8; AVT-STB-301 | Accelerated Impurity A on R03 reached 0.46% at 6 months (from 0.06%), a significant change under ICH Q1A(R2); 'within specification' is not the test. IR point 4 asks for confirmation that this was treated as a significant change and that STB-AVI401-003 is the complete response. 3.2.P.8 says the intermediate study was initiated because of the accelerated change, while AVT-STB-301 says it was a standing zone II precaution 'not in response to a finding'. The two controlled records conflict. | Tomas Li, QC Stability (with Regulatory CMC) | 2027-03-20 | IR response incomplete; contradictory records unresolved. | Documented significant-change assessment; reconciled intermediate-study rationale; confirmation that STB-AVI401-003 is the complete response. | Open |  | Viktor Takacs
QC-10 | Regulatory Handoff!A6:F6; AVI-401 Accelerated and Intermediate Results!Laboratory Events | IR point 4 asks for the assignable cause of LAB-2025-114, the confirmatory replacement result, and whether the same mobile-phase preparation error could have affected any other reported sequence in that campaign. The workbook states no campaign assessment is needed, which does not answer the question. | Quality Investigations (with QC Stability) | 2027-03-20 | IR response incomplete. | LAB-2025-114 investigation report, campaign/sequence impact review, and confirmatory result on the retained sample. | Open |  | Viktor Takacs
QC-11 | Regulatory Handoff!A7:F7; CC-AVI401-017; HFC-QN-2026-074 | IR point 3 requires the OTR used for registered overwrap BF-51 at a humidity relevant to 25 C/60% RH and how residual headspace oxygen in the 100 mL and 250 mL fills was controlled or measured, citing the document and page if held in supplier files or the container-compatibility report. The workbook cites only the current stability summary. Open CC-AVI401-017 proposes alternate HF-55 (OTR 3.8 vs BF-51 2.4 at 23 C/65% RH) but is not approved or authorized and must not be represented as the registered package. | MSAT (with Regulatory CMC and QC Stability) | 2027-03-20 | IR response incomplete; unapproved material must not be represented as registered. | Document/page citation for BF-51 OTR and residual-headspace control/measurement; confirmation of the registered overwrap and CC-AVI401-017 status. | Open |  | Viktor Takacs
QC-12 | Chain and Controls!A1:L7; AVT-STB-102-A4; AVT-SPEC-018 | The testing-chain list is incomplete and mis-scoped. Per AVT-STB-102-A4 the chain is the storage chamber plus every method, instrument and reference standard in AVT-SPEC-018. Missing: PH-03 + RS-BUF-021, HPLC-04, OSM-02, PM-01 + RS-PSL-012, INC-03, RS-IMPA-009, RS-IMPB-006 and the method revalidations. Included but out of scope: UV-02, GC-01 and KF-01. | Tomas Li, QC Stability | 2027-02-26 | Chain clearance and pull authorization withheld. | Complete chain list with qualified-state evidence for every asset and removal of out-of-scope assets, reconciled to AVT-STB-102-A4. | Open |  | Viktor Takacs
QC-13 | Control!B12; Control!C12 | The working basis is not supported. It states the 24-month dataset is expected to support the open authority response, but IR point 7 routes the 24-month data to COM-AVI401-008, and it states the calibration package supports the chain, but CHM-25-03, RS-AVR-014 and CCI-02 are not current or are misstated. | Tomas Li, QC Stability | 2027-02-26 | Functional approval withheld. | Corrected working basis consistent with the IR and the verified testing chain. | Open |  | Viktor Takacs
QC-14 | Chain and Controls!A2:F4; Execution Sequence!A2:F8 | Potential lapses of the qualified state (CHM-25-03 requalification, RS-AVR-014 expiry, CCI-02 calibration) require an independent QA assessment and, if confirmed, deviation handling before data can be relied on. | Leena Rao, QA Product Lead (with QA) | 2027-02-26 | Final QC disposition cannot release data until the QA assessment is recorded. | QA assessment of qualified-state impact and any linked deviation/CAPA records. | Open |  | Viktor Takacs
QC-15 | Control!A9:C12; QC Disposition!A2:B13 | The corrected package must be returned for QC re-verification before the pull is authorized and before verified data move to QA or Regulatory. This is a QC functional hold, not a rejection of the study. | Viktor Takacs, QC reviewer | Before pull and before handoff | Pull, dataset release and regulatory handoff remain withheld until re-verification is recorded. | Corrected workbook with QC-01 to QC-14 closed and evidence linked; QC re-verification entry. | Open |  | Viktor Takacs

## QC Disposition
Decision field | QC entry
Disposition | Not approved - returned for correction (hold). Pull, dataset release and regulatory handoff withheld while QC-01 to QC-15 are open.
Decision date | 2027-02-08
Reviewer | Viktor Takacs
Scope approved | None. No part of the pull, dataset release or regulatory handoff is approved by this review.
Restrictions | QC-01 lot/presentation mapping; QC-02 CHM-25-03 qualified state; QC-03 RS-AVR-014 expiry; QC-04 CCI-02 calibration; QC-05 dataset lock; QC-06/07/08/09/10/11 regulatory handoff; QC-12 testing-chain completeness; QC-13 working basis; QC-14 QA consultation. No data release to QA or Regulatory and no pull authorization until these close and QC-15 re-verification is recorded.
Pull authorization | Not authorized - withheld pending QC-01, QC-02, QC-12 and the QC-14 QA assessment.
Dataset release | Not released - the 24-month dataset is incomplete and the testing chain is not cleared.
Regulatory handoff | Not cleared - the written response must be re-scoped (QC-06) and the COM-AVI401-008 milestone re-baselined (QC-07).
Open action IDs | QC-01, QC-02, QC-03, QC-04, QC-05, QC-06, QC-07, QC-08, QC-09, QC-10, QC-11, QC-12, QC-13, QC-14, QC-15
Evidence basis | Tomas baseline workbook; STB-AVI401-002 Study Status and Long Term Results; 3.2.P.8 (AVT-CMC-038 v03); AVT-STB-301; AVT-STB-102-A4; AVT-SPEC-018; AVT-SOP-018/040/045/051/054; AVT-RS-088; AVT-RS-093; AVT-VAL-316; AVT-VAL-338/344/347/348/350/352/355/358; MER-2026-4587; MER-2026-5512; MER-2026-8014; MER-2026-6108/6402/6799/8830/9014/9221; CC-2023-004; CC-AVI401-017; HFC-QN-2026-074; HA-AVI401-IR-2027-014; AVI-401 Accelerated and Intermediate Results.
QA consultation | Required - QA assessment of the CHM-25-03 requalification lapse, the RS-AVR-014 expiry and the CCI-02 calibration expiry affecting the qualified state (QC-14).
Decision statement | Reviewed by Viktor Takacs, QC, on 2027-02-08 against the evidence listed above. The baseline workbook is not functionally approved. Tomas Li's baseline entries are preserved; QC findings and send-backs are recorded in the QC fields, cell comments and Review Actions. The accountable functions must close QC-01 to QC-15 and return the corrected package for QC re-verification before the pull is authorized and before any verified data move onward to QA or Regulatory.
Note on B2: QC functional hold (Viktor Takacs, 2027-02-08). Not a study rejection. Return after QC-01 to QC-14 are closed; see Review Actions.