## Control
Field | Tomas baseline | QC final
Prepared by | Tomas Li, QC Stability
Prepared | 2027-02-06
Study | STB-AVI401-002
Decision package | 24-month pull, testing, and authority response
QC decision owner | Viktor Takacs
Required decision date | 2027-02-08
Tomas recommendation | Authorize the 1 March pull and the full campaign. Use the current calibration package and routine due-month conventions. Lock the primary dataset for the 20 March response and append late CCI data to COM-AVI401-008.
QC disposition
Restrictions that remain active
Next attributable QC review trigger

## Operation Gates
Operation | Planned date | Tomas baseline decision | Baseline dependency | QC decision | QC basis / correction | Accountable owner | Supporting function | Due / gate | Objective closure evidence | Controlled source locator | QC comment ref
Physical pull and receipt | 2027-03-01 | GO | CHM-25-03 calibration current through 2027-12-05
Appearance / pH | 2027-03-02 to 2027-03-04 | GO | Routine bench sequence
Osmolality / particulate matter | 2027-03-08 to 2027-03-12 | GO | Current instruments and standards
Assay | 2027-03-15 to 2027-03-18 | GO | RS-AVR-014 effective 2025-05-03
Impurities | 2027-03-22 to 2027-03-26 | GO | MTH-HPLC-012 current through June 2027
Sterility | 2027-03-02 to 2027-03-16 | GO | Routine incubation
Container closure integrity | 2027-04-13 to 2027-04-14 | GO | CCI-02 due April 2027
Complete dataset lock / QC release | 2027-03-19 | GO | Primary results complete; late CCI may follow
Written-response evidence handoff | 2027-03-19 | GO | Use complete 24-month package
COM-AVI401-008 verified-data handoff | 2027-04-29 | GO | Reuse the response package

## Qualified Chain
Specification test | Method | Instrument | Reference standard | Tomas baseline state | QC decision | QC basis / correction | Accountable owner | Supporting function | Due / gate | Objective closure evidence | Controlled source locator | QC comment ref
Appearance | MTH-VIS-002 | UV-02 backup | N/A | Current
pH | MTH-PHY-004 | PH-03 | Not listed | Current
Assay | MTH-HPLC-011 | HPLC-04 | RS-AVR-014 | Current to 2027-05-03
Impurity A | MTH-HPLC-012 | HPLC-04 | RS-AVR-014 | Current to 2027-05-03
Impurity B | MTH-HPLC-012 | HPLC-04 | Not listed | Current
Total impurities | MTH-HPLC-012 | HPLC-04 | Not listed | Current
Osmolality | MTH-PHY-009 | OSM-02 | RS-OSM-004 | Current
Particulate matter | MTH-PHY-015 | PM-01 | Not listed | Current
Container closure integrity | MTH-CCI-003 | CCI-02 | N/A | Current in due month
Sterility | MTH-MIC-001 | INC-03 | N/A | Current
Storage | Protocol appendix | CHM-25-03 | N/A | Calibration demonstrates qualification
Contingency assets | Various | GC-01 / KF-01 | N/A | Include in clearance

## Impurity A Analysis
Lot | Presentation | Data through | Tomas 24 m projection | Tomas 36 m projection | Tomas residual SE | Tomas one-sided upper bound at 36 m | Tomas conclusion | QC 24 m projection | QC 36 m projection | QC residual SE | QC one-sided upper bound at 24 m | QC one-sided upper bound at 36 m | QC supported shelf life / interpretation | QC source locator | QC comment ref
AVI401-R01 | 100 mL | 18 months | 0.31 | 0.46 |  |  | Supports 36 months
AVI401-R02 | 250 mL | 18 months | 0.3 | 0.45 |  |  | Worst case; supports 36 months
AVI401-R03 | 500 mL | 18 months | 0.36 | 0.49 |  |  | Supports 36 months

## Authority Response
Request | Tomas baseline response / evidence | Baseline owner | QC decision | QC basis / correction | Accountable owner | Supporting function | Due / gate | Objective closure evidence | Controlled source locator | QC comment ref
1. P.7 bookmarking and pagination | No QC action | Regulatory CMC
2. Impurity A trend and shelf life | Attach refreshed 24-month projections | QC Stability
3. Overwrap and headspace support | Current stability summary confirms control | MSAT / Regulatory CMC
4. Accelerated significant change | 0.46% is within specification; no action | QC Stability
5. Filtration and hold coverage | Validation report references | Validation / MSAT
6. Infusion and leachables | Product is already registered | CMC / Regulatory
7. Invalidated Impurity B run | Replacement result closes the event | QC Stability

## Action Ledger
Action ID | Linked sheet / cells | Decision or deficiency | Accountable owner | Supporting function | Due / gate | Objective closure evidence | Controlled source locator | Status | Closure record / next review trigger | QC reviewer
ACT-01
ACT-02
ACT-03
ACT-04
ACT-05
ACT-06
ACT-07
ACT-08
ACT-09
ACT-10
ACT-11
ACT-12
ACT-13
ACT-14
ACT-15
ACT-16
ACT-17
ACT-18
ACT-19
ACT-20

## QC Disposition
Decision field | QC entry
Disposition
Decision date
Reviewer | Viktor Takacs
Physical pull decision
Testing decisions
Complete dataset release
Written-response evidence handoff
COM-AVI401-008 handoff
Open action IDs by gate
Evidence basis
Next attributable QC review trigger
Decision statement